## Implementation Plan
GPS INSIGHT IMPLEMENTATION PLAN |  |  |  | Customer Name:
Start Date:
End Date:
Status | 1. Contract & Invoicing | Notes | Date Scheduled | Date Completed | Tools | Resources
a. Contract & Handoff
| Contract Execution Date: |  |  |  |  | Sales, Account Manager
| Contract Term: |  |  |  |  | Sales, Account Manager
| Contract Expiration Date: |  |  |  |  | Sales, Account Manager
| Implementation Deadline Date: |  |  |  |  | Sales, Account Manager
| Total Device Count: |  |  |  |  | Sales, Account Manager
| Total Asset Count: |  |  |  |  | Sales, Account Manager
| Accessories: |  |  |  |  | Sales, Account Manager
| Installation Terms and Conditions signed by Customer if doing third party install. |  |  |  |  | Sales, Account Manager, Customer
| Sales to update NS, provide Impact Grid, contract, pricing, and any other relevant materials to Account Manager to ensure successful handoff. |  |  |  |  | Sales, Account Manager, Customer
| Sales to introduce Customer to assigned Account Manager. |  |  |  |  | Sales
| Account Manager to provide implementation plan to customer if needed. Determine if any other documents are required. |  |  |  |  | Account Manager
b. Invoicing
| Meeting between Customer Fleet Project Manager, Customer Accounting, GPSI Sales, GPSI Accounting, GPSI Install Coordinator, GPSI Account Manager to determine invoicing process and requirements. |  |  |  |  | Sales, Account Manager, Customer Accounting, GPSI Accounting
| Discuss invoicing process with Customer: 1. Who should invoices be sent to? Are there any special invoice routing instructions needed? 2. Discuss new PO creation process and schedule, including: frequency, how long a PO takes to be issued, who to contact for new PO, correct PO process etc. 3. Consider the Purchase Orders needed to cover: a. Reoccurring monthly service fee b. Initial Installation c. Device maintenance/troubleshooting d. New devices purchases e. New Installation projects |  |  |  |  | Sales, Account Manager, Customer
| Verify invoicing process is working correctly after first month's bill. Coordinate meeting between GPSI Accounting and Customer Accounting as needed to discuss/resolve any invoice issues. |  |  |  |  | Customer, Account Manager
Status | 2. Project Initiation | Notes | Date Scheduled | Date Completed | Tools | Resources
a. Implementation Kick-off
| Kick-off call with the Customer and Account Manager. Customer identifies key contacts and provides contact information: Fleet Project Manager, Installation Manager, Department contacts, Fleet manager(s), Training Coordinator, etc. |  |  |  |  | Customer, Sales, Account Manager
| Discuss importance of a Point Person taking ownership of project at customer site to ensure program's success, including coordinating and communicating new telematics program. Discuss Communication schedule. Solicit Customer feedback regarding any concern they may have around installation/implementation. |  |  |  |  | Account Manager, Customer
| Provide an overview of GPSI Account Management and our role to Customer Fleet Project Manager. See Account Management Section below. |  |  |  |  | Account Manager, Customer
| Provide implementation Overview to Fleet Project Manager. Gain understanding on any time constraints. |  |  |  |  | Account Manager, Customer
| Discuss Training Options for both Admins and Users. See Training Section below. |  |  |  |  | Account Manager, Customer
| Verify Customer telematics goals and outline GPSI tools to utilize. |  |  |  |  | Account Manager
| Kick-off email sent to Customer with links to Implementation plan, vehicle list, communication plan/materials, and training. |  |  |  |  | Account Manager
b. Installation Overview
| Schedule a call to discuss Installation in-depth. See Installation Section for more information. |  |  |  |  | Account Manager, Customer
| Account Manager will be providing a biweekly installation/project update to customer, installs and GPSI Sales. |  |  |  |  | Account Manager
c. Integration Overview
| Provide an overview about GPSI integration capabilities such as APIs, Webhooks, fuel cards or GIS etc. See Integration section for more information. |  |  |  |  | Account Manager, Customer
| Send Customer link to API and Webhook Integration information in Help Center. |  |  |  |  | Account Manager
| Determine integration work that may be required, timeline and deadlines. |  |  |  |  | Account Manager
Status | 3. Order & Fulfillment | Notes | Date Scheduled | Date Completed | Tools | Resources
a. Pre-Order
| Sales sends Vehicle List template to Customer. |  |  |  |  | Account Manager
| Customer emails Installs a vetted vehicle list to Sales to include (per vehicle) the following: Vehicle Label, VIN #, Year, Make, Model, Department, Install Address, Install Contact info (Name, Phone Number, Email Address), Full Ship to Address and Ship to Contact Info (Name, Phone Number, Email Address). |  |  |  |  | Customer
| It is recommended that Sales uses the KB Tool "Find a Device" to determine appropriate device type, cables and add-ons based on vehicle year/make/model to create Order. Sales sends the completed Vehicle List to Installs/Sales Engineer for review. Certain vehicles, such as 16 Pin Mack Trucks require special cables. |  |  |  |  | Sales, Install Coordinator
| Sales sends vehicle list with device recommendations to Installs. GPSI Installs reviews vehicle list and provides feedback on unit type/equipment for Order to GPSI Sales. |  |  |  |  | Install Coordinator
| Vehicle List Spreadsheet provided to Customer for approval outlining vehicle devices, accessory cable requirements and assignments for Installation. a. In professional installation scenario Sales creates a Sales Admin Installation Request form and verifies it referencing Vehicle List Spreadsheet. b. In self-installation scenarios, Sales would send Vehicle List to Customer Project Manager to provide to installers to refer to during installation. |  |  |  |  | Install Coordinator, Sales
| Customer Accounting begins process to create the two POs; by Department one for Installation and Hardware and another for Service. |  |  |  |  | Customer
| Installs updates the spreadsheet with the two POs for every vehicle and emails the updated spreadsheet to GPSI Sales for Sales Order creation purposes. *Units will not ship without both POs* |  |  |  |  | Install Coordinator
b. Order
| GPSI Sales creates Estimate for device orders. This is sent to customer for approval. |  |  |  |  | Sales
| Customer approves Estimate. |  |  |  |  | Customer
| Customer emails spreadsheet to all site contacts to make them aware of their upcoming shipments. Any install changes must be handled internally by Customer and authorized by GPSI Installer; to include moving of hardware from one location to another. |  |  |  |  | Customer
c. Fulfillment
| Vehicle List with device/cable requirements sent to Fulfillment for printing and inclusion in box. |  |  |  |  | Sales
| Shipment date/times may vary and are dependent on other variables such as time of order entry, size of order, scripting, programming, inventory issues, team bandwidth and other orders ahead of yours. GPSI Fulfillment begins shipping orders via standard FedEx 2 Day Air by Default unless overwise instructed. |  |  |  |  | Fulfillment
| Primary contact in NS is sent Shipment Tracking Information |  |  |  |  | Fulfillment
| Verify Customer has received all GPS Units |  |  |  |  | Account Manager
Status | 4. Installation | Notes | Date Scheduled | Date Completed | Tools | Resources
a. Installation Overview
| Project Tracking Installation Start Date: Installation End Date: Total Installed: (End Date for main scheduled group of installs, not including follow up installs) |  |  |  |  | Account Manager
| Installation Meeting for Account Manager, GPSI Installation Coordinator and Customer Fleet Project Manager to set installation expectations, discuss vehicle availability, special wiring/mounting instructions, PPEs, site restrictions/access, and identify installation deployment type (assembly line, staged vehicles, etc.), vehicle keys. |  |  |  |  | Account Manager, Customer, Install Coordinator
| Provide an overview of the installation process: 1. Devices shipped to install location 2. Packing/assembly specifics 3. Installation 4. Installation verification 5. Vehicle registration (Installs must be called in to GPSI Support) Recommend install is performed during GPSI Support business hours 5 AM-6 PM. If not during normal hours, GPSI Support Manager must be notified to ensure proper coverage. |  |  |  |  | Account Manager, Customer
| Discuss post installation Device Maintenance program requirements and provide recommendations regarding GPSI troubleshooting tools and processes. |  |  |  |  | Account Manager, Customer
| Follow up Installation costs traditionally differ from Initial Deployment, discuss standard Installation fees. |  |  |  |  | Account Manager
| We ship everything FedEx 2 day by default. Verify that is acceptable to customer. |  |  |  |  | Account Manager
| Determine which type of installation will be performed: 1. Third party installer - GPSI Coordinated 2. Self-Install |  |  |  |  | Account Manager, Customer
This section applies to Self-Install Only:
| If self-install is chosen, Account Manager sends install guides/video links to Customer. Account Manager verifies Customer has viewed video/materials and is comfortable performing the installation. If not, Account Manager schedules call with Customer, and Installation team adds any clarity that is needed. |  |  |  |  | Account Manager, Customer
| Customer signs off on Self-Install Terms and Conditions. |  |  |  |  | Customer
| Customer provides Vehicle List to Account Manager include (per vehicle) the following: Vehicle Label, VIN #, Year, Make, Model, Department, Add ons: (PTO, Driver ID), Install Location address/contact info, Full Ship to Address/contact info. |  |  |  |  | Customer
| GPSI Installs assess Vehicle List and provides device recommendations. |  |  |  |  | Account Manager, Install Coordinator
| If applicable, GPSI Installs provides recommendations on unit type/installation method to Account Manager for Customer. |  |  |  |  | Install Coordinator
| Warranty requires that install verification is performed after each installation by calling 866-477-4321 x2 while the installer is at the vehicle. Registration will be handled by GPSI Support at that time. |  |  |  |  | Installer, Support
b. Preparation for GPSI Install
| GPSI Installer creates installation route with installation dates and times; first install date will be 1.5-2 weeks from Order entry, if possible. |  |  |  |  | Installer
| GPSI Installer emails updated spreadsheet with install site scheduled dates and times to Customer and Installs. |  |  |  |  | Installer
| One to two business days prior to each schedule locations appointment the Preferred installation vendor will reach out to the site contact in the spreadsheet to remind them of the schedule appointment, number of techs arriving, and number of vehicle they expect to touch per day while they’re onsite. |  |  |  |  | Installer, Customer
| Preferred installation vendor installs, verifies and registers devices. If needed, GPSI Tech Support will also be available to verify and register devices. |  |  |  |  | Installer
| If a vehicle does not arrive to a scheduled appointment Preferred installation vendor will email GPSIAM, Installation Coordinator, key customer personal involved (Customer Deployment Project Manager) asking customer if the vehicle can be traveled to the next install location in the technicians route. |  |  |  |  | Installer
| If the vehicle cannot be made available, the vehicle will be flagged for follow-up and after completion of the initial roll-out all follow-up vehicles will be combined and placed into a new spreadsheet which is then sent to the key customer personal involved (Customer Deployment Project Manager) for updated install location and site contact information. |  |  |  |  | Install Coordinator
c. Installation Begins
| Installer registers the installed vehicles in the GPS Insight Portal. (Vehicles may take up to 24 hours to be viewed in GPS Insight system.) |  |  |  |  | Installer
| Weekly updates will be sent to Customer/Sales regarding install progress. Account Manager to coordinate with Installation Coordinator regarding when Installation spreadsheet needs to be updated in order to provide this update per schedule. |  |  |  |  | Account Manager
d. Installation Verification
| GPSI Support verifies device reporting across the entire fleet. GPSI Account Manager to request this. |  |  |  |  | Account Manager, Support
| Install Coordinator audits installation and identifies any remaining items to be accomplished (e.g., total installed vs. vehicle list, units not installed, vehicles unavailable) and communicates to Customer. |  |  |  |  | Install Coordinator
| Install Coordinator begins coordinating any follow up installation work required. |  |  |  |  | Install Coordinator
| GPSI Support verifies optimal device reporting. |  |  |  |  | Account Manager
e. Installation Complete
| Install Coordinator communicates to Customer and Account Manager that installation is complete. |  |  |  |  | Install Coordinator
Status | 5. Account Set Up | Notes | Date Scheduled | Date Completed | Tools | Resources
Account Set Up Overview
Overview: The majority of the account set up can be performed prior to vehicles being added to the account, and this can also be done in parallel with installation. | Note: Hierarchy Vehicle Groups is an advanced way to organize vehicles and requires set up assistance. It is to be used for the organization of vehicles for fleets over 100 that have sophisticated needs. This includes using API's to move vehicles, custom report groups, scheduled report/alerts distribution lists, and escalating alerts. Note: The majority mid-market and small business Customers will be satisfied using Vehicle Groups. Customers utilizing Hierarchy may also occasionally use Vehicle groups, because they are quick to set up, for specific needs like wanting to see unrelated vehicles grouped together. |  | Note: Hierarchy Vehicle Groups is an advanced way to organize vehicles and requires set up assistance. It is to be used for the organization of vehicles for fleets over 100 that have sophisticated needs. This includes using API's to move vehicles, custom report groups, scheduled report/alerts distribution lists, and escalating alerts. Note: The majority mid-market and small business Customers will be satisfied using Vehicle Groups. Customers utilizing Hierarchy may also occasionally use Vehicle groups, because they are quick to set up, for specific needs like wanting to see unrelated vehicles grouped together. | Note: Hierarchy Vehicle Groups is an advanced way to organize vehicles and requires set up assistance. It is to be used for the organization of vehicles for fleets over 100 that have sophisticated needs. This includes using API's to move vehicles, custom report groups, scheduled report/alerts distribution lists, and escalating alerts. Note: The majority mid-market and small business Customers will be satisfied using Vehicle Groups. Customers utilizing Hierarchy may also occasionally use Vehicle groups, because they are quick to set up, for specific needs like wanting to see unrelated vehicles grouped together. | Note: Hierarchy Vehicle Groups is an advanced way to organize vehicles and requires set up assistance. It is to be used for the organization of vehicles for fleets over 100 that have sophisticated needs. This includes using API's to move vehicles, custom report groups, scheduled report/alerts distribution lists, and escalating alerts. Note: The majority mid-market and small business Customers will be satisfied using Vehicle Groups. Customers utilizing Hierarchy may also occasionally use Vehicle groups, because they are quick to set up, for specific needs like wanting to see unrelated vehicles grouped together. | Note: Hierarchy Vehicle Groups is an advanced way to organize vehicles and requires set up assistance. It is to be used for the organization of vehicles for fleets over 100 that have sophisticated needs. This includes using API's to move vehicles, custom report groups, scheduled report/alerts distribution lists, and escalating alerts. Note: The majority mid-market and small business Customers will be satisfied using Vehicle Groups. Customers utilizing Hierarchy may also occasionally use Vehicle groups, because they are quick to set up, for specific needs like wanting to see unrelated vehicles grouped together.
| Customer to define contacts in each department for account set up and the Fleet manager in each Department. Customer is responsible for pulling in and coordinating with department contacts for training/account set up as needed. |  |  |  |  | Account Manager, Customer
| Account Setup overview: a. Hierarchy b. Vehicle Groups c. Manage Vehicles d. Spreadsheet Upload e. Attributes f. Users g. Dashboards h. Drivers I. Scheduled Reports j. Scheduled Alerts k. Landmarks |  |  |  |  | Account Manager, Customer
| Recommend Account Admin takes Training Courses 1 & 2 in Help Center. Review Help Center Resources for Account setup, Support, Training etc. |  |  |  | "Help Center" in Customer's portal | Account Manager, Customer
a. Hierarchy
Overview: Hierarchy Vehicle Groups is an advanced way to organize vehicles and requires set up assistance. This feature is for enterprise customers that have sophisticated needs. This set up includes building multiple Trees, custom report groups, scheduled report/alerts distribution lists, and escalating alerts. The Hierarchy is designed to allow large fleets to mirror their fleet organization structures within the GPS Insight application. Examples of hierarchy could be organization structures, geographic, by business unit, by type of vehicle, etc. After the Hierarchy structure is in place and vehicles are assigned to it, users can use these hierarchy vehicle groups throughout the GPS Insight application. Hierarchy vehicle groups can be used in the dashboard and maps. They can also be used to schedule reports and to configure escalating alerts. Best of all, vehicles assignments within the Hierarchy can be easily modified when vehicles come in and out of the fleet or move within the organization. In addition, the user hierarchy enables users to manage other users, vehicles and the hierarchy as assigned to them by the main Account Administrator. | Note: Hierarchy Vehicle Groups is an advanced way to organize vehicles and requires set up assistance. It is to be used for the organization of vehicles for fleets over 100 that have sophisticated needs. This includes using API's to move vehicles, custom report groups, scheduled report/alerts distribution lists, and escalating alerts. Note: The majority mid-market and small business Customers will be satisfied using Vehicle Groups. Customers utilizing Hierarchy may also occasionally use Vehicle groups, because they are quick to set up, for specific needs like wanting to see unrelated vehicles grouped together. |  | Note: Hierarchy Vehicle Groups is an advanced way to organize vehicles and requires set up assistance. It is to be used for the organization of vehicles for fleets over 100 that have sophisticated needs. This includes using API's to move vehicles, custom report groups, scheduled report/alerts distribution lists, and escalating alerts. Note: The majority mid-market and small business Customers will be satisfied using Vehicle Groups. Customers utilizing Hierarchy may also occasionally use Vehicle groups, because they are quick to set up, for specific needs like wanting to see unrelated vehicles grouped together. | Note: Hierarchy Vehicle Groups is an advanced way to organize vehicles and requires set up assistance. It is to be used for the organization of vehicles for fleets over 100 that have sophisticated needs. This includes using API's to move vehicles, custom report groups, scheduled report/alerts distribution lists, and escalating alerts. Note: The majority mid-market and small business Customers will be satisfied using Vehicle Groups. Customers utilizing Hierarchy may also occasionally use Vehicle groups, because they are quick to set up, for specific needs like wanting to see unrelated vehicles grouped together. | Note: Hierarchy Vehicle Groups is an advanced way to organize vehicles and requires set up assistance. It is to be used for the organization of vehicles for fleets over 100 that have sophisticated needs. This includes using API's to move vehicles, custom report groups, scheduled report/alerts distribution lists, and escalating alerts. Note: The majority mid-market and small business Customers will be satisfied using Vehicle Groups. Customers utilizing Hierarchy may also occasionally use Vehicle groups, because they are quick to set up, for specific needs like wanting to see unrelated vehicles grouped together. | Note: Hierarchy Vehicle Groups is an advanced way to organize vehicles and requires set up assistance. It is to be used for the organization of vehicles for fleets over 100 that have sophisticated needs. This includes using API's to move vehicles, custom report groups, scheduled report/alerts distribution lists, and escalating alerts. Note: The majority mid-market and small business Customers will be satisfied using Vehicle Groups. Customers utilizing Hierarchy may also occasionally use Vehicle groups, because they are quick to set up, for specific needs like wanting to see unrelated vehicles grouped together.
| Account Manager to provide training on Hierarchy to Customer. See training topics below: |  |  |  |  | Account Manager
| Account Manager to send Hierarchy Overview document to Customer. |  |  |  |  | Account Manager
| Customer to Create hierarchy(s). |  |  |  |  | Account Manager, Customer
Account Manager to review Hierarchy structure and trees. Make recommendations if appropriate.
| Hierarchy permissions: Add permission to edit the Hierarchy to users. |  |  |  |  | Account Manager, Customer
| Vehicles: Add and assign vehicles. Note: The assignment of vehicles will be an ongoing task as vehicles are installed and added to the system. Can be performed manually or via spreadsheet upload. |  |  |  |  | Account Manager, Customer
| Account Manager to send User Hierarchy Overview document to Fleet Project Manager. |  |  |  |  | Account Manager, Customer
| User Hierarchy: Add and assign users to Hierarchy Nodes. Show how to set up and administer Department User Admins. |  |  |  |  | Account Manager, Customer
| Drivers: Add and assign drivers to Hierarchy tree nodes. Note: Drivers must be assigned to Hierarchies and/or Driver Groups in order for customers to see driver based reports. |  |  |  |  | Account Manager, Customer
| Landmarks: Discuss and show how to add landmarks to tree nodes. |  |  |  |  | Account Manager, Customer
| Attributes: Discuss attributes in relation to Hierarchy email alerts and reports. |  |  |  |  | Account Manager, Customer
| Alerts: Set up notification attributes for alerts. |  |  |  |  | Account Manager, Customer
| Reports: Create custom Hierarchy report groups. |  |  |  |  | Account Manager, Customer
b. Vehicle Groups
Overview: Customers utilizing Hierarchy may also occasionally use Vehicle groups because they are quick to set up and allow for specific grouping needs (e.g., see unrelated vehicles grouped together). This should not be the main way an enterprise customer groups all of their vehicles.
| Provide training on Vehicle Groups to Customer. See training topics below: |  |  |  |  | Account Manager, Customer
| Create vehicle groups. |  |  |  |  | Account Manager, Customer
| Add and assign vehicles. |  |  |  |  | Account Manager, Customer
| Set vehicle group permissions. |  |  |  |  | Account Manager, Customer
c. Vehicles
| Provide training and an overview of Manage Vehicles. See training topics below: |  |  |  |  | Account Manager, Customer
| Register new vehicle. |  |  |  |  | Account Manager, Customer
| Deactivate a device. |  |  |  |  | Account Manager, Customer
| Edit vehicle details. |  |  |  |  | Account Manager, Customer
| Assign/Change Hierarchy membership. |  |  |  |  | Account Manager, Customer
| Manage map icons. |  |  |  |  | Account Manager, Customer
d. Spreadsheet Upload
Overview: Customers can utilize this functionality to update practically anything they have added to the system via an Excel/csv file using spreadsheet upload. This includes vehicles, users, drivers, driver assignments, and vehicle groups. This is the fastest way to add and change data in GPS Insight (aside from APIs).
| Provide training and overview on Spreadsheet Upload and Export to Customer. |  |  |  |  | Account Manager, Customer
| Account Manager to send Spreadsheet Upload document to Customer. |  |  |  |  | Account Manager
| To explore options, go to "Account" tab, and select Manage Vehicles, Drivers, or Users. Select the option to "Update/export items using a spreadsheet" to see choices. There are spreadsheet examples for each upload that the Customer can use as a template. |  |  |  |  | Account Manager, Customer
e. Attributes
Overview: How to add, use, and edit (manually and spreadsheet upload). Where they can be used: Hierarchy Alerts and Reports, Report column, Dashlets (closest to/vehicle selector), Mapping, Alert notifications.
| Provide training and overview on Attributes. See training topics below: |  |  |  |  | Account Manager, Customer
| Hierarchy. |  |  |  |  | Account Manager, Customer
| Vehicle. |  |  |  |  | Account Manager, Customer
| Driver. |  |  |  |  | Account Manager, Customer
| Landmark. |  |  |  |  | Account Manager, Customer
| Customer will be responsible for adding attributes for Departments as needed. |  |  |  |  | Customer
f. Users
Overview: How to add users, permissions and dashboards to Customer, such as how to create user menu templates, clone users/assign templates, and use spreadsheet upload to update. Review User Planning section in Help Center. For many users permissions/dashboards; it is recommended to create a generic user and set all the permissions and create default dashboards, and then clone that user. Spreadsheet upload should then be used to assign the vehicle group access to each new user.
| GPSI will provide Customer with an overview of User Planning (Help Center) and Permissions (Access and Menu), Dashboards and Templates, Cloning, User Hierarchy Permission assignment. |  |  |  |  | Account Manager, Customer
| Account Manager will provide a spreadsheet of required user information to Customer. Spreadsheet includes: Username, Full Name, email, Time zone, Vehicle Hierarchy permission, Landmark Groups, Menu and Access permission, User Hierarchy permission |  |  |  |  | Account Manager
| Customer to determine standard, generic user types and set menu/access permissions and dashboard for each generic user. Example: Advanced Admin, Basic User, Dispatcher. Then, clone generic users for all users. |  |  |  |  | Customer
| Create new users. |  |  |  |  | Account Manager, Customer
| Set access permissions. |  |  |  |  | Account Manager, Customer
| Set menu permissions. |  |  |  |  | Account Manager, Customer
| Create access permission templates and assign to users via spreadsheet upload |  |  |  |  | Account Manager, Customer
| Assign hierarchy/vehicles/groups/drivers to users manually and via spreadsheet upload. |  |  |  |  | Account Manager, Customer
g. Dashboards
| Provide training and overview on Dashboards. See training topics below: |  |  |  |  | Account Manager, Customer
| Provide Customer with template(s) showing dashboard recommendations from Help Center. Customer to Determine default dashboards per user level and type. |  |  |  |  | Account Manager
| GPSI will provide Customer with a spreadsheet for assigning dashboards to users |  |  |  |  | Account Manager, Customer
| GPSI will assign the dashboards to users via spreadsheet upload |  |  |  |  | Account Manager, Customer
| Create a new dashboard. |  |  |  |  | Account Manager, Customer
| Set dashboard configurations/edit options. |  |  |  |  | Account Manager, Customer
| Save a dashboard and assign to tabs. |  |  |  |  | Account Manager, Customer
h. Drivers
| Provide training and an overview of Drivers to Customer. |  |  |  |  | Account Manager, Customer
| Create new drivers. |  |  |  |  | Account Manager, Customer
| Assign driver to vehicle. |  |  |  |  | Account Manager, Customer
| Create driver groups. |  |  |  |  | Account Manager, Customer
| Set Driver Alert method (email/text) |  |  |  |  | Account Manager, Customer
| Review driver assignment update methods via portal, spreadsheet upload, API etc. |  |  |  |  | Account Manager, Customer
i. Scheduled Reports
| Provide an overview of scheduled reports to Customer, including scheduled report options, schedule, and settings. Discuss overall Reports and Alerts strategy, where they receive the reports via email phase 1, then schedule alerts phase 2. |  |  |  |  | Account Manager, Customer
| Provide Customer with Alerts and Reports Strategy document and review with them. |  |  |  |  | Account Manager, Customer
| Recommend scheduled reports to be set based on Customer's goals and KPIs. |  |  |  |  | Account Manager
| Customer determines which reports to schedule and frequency, by type per user/location in line with goals. |  |  |  |  | Customer
| Report distribution lists can be sent through Hierarchy Attributes or to a user entered email address. If Hierarchy Attributes are going to be used, the Email addresses need to be added to the Distribution Attribute (which will need to be created) for each node. |  |  |  |  | Account Manager, Customer
| Customer determines distribution list for reports, including vehicle group and users to receive. |  |  |  |  | Customer
| Assist Customer in scheduling initial reports. Performance, Speed, Idle, Fleet Utilization. |  |  |  |  | Account Manager, Customer
j. Alerts
| Provide an overview of alerts to Customer, including alert options, settings, and recommendations. Discuss overall Reports and Alerts strategy, where they receive the reports via email phase 1, then schedule alerts phase 2. Alerts should be set with a specific action in mind when the individual receives the alert. |  |  |  |  | Account Manager, Customer
| Provide Customer with Alerts and Reports Strategy document and review with them. |  |  |  |  | Account Manager, Customer
| Recommend alerts to be set based on Customer's goals and KPIs. |  |  |  |  | Account Manager
| Customer determines which alerts to schedule and notification frequency, by type per user/location in line with goals. |  |  |  |  | Customer
| Alert distribution lists can be sent through Hierarchy Attributes or to a user entered email address. If Hierarchy Attributes are going to be used, the Email addresses need to be added to the Distribution Attribute (which will need to be created) for each node. |  |  |  |  | Account Manager, Customer
| Customer determines distribution list for alerts, including vehicle group and users to receive. |  |  |  |  | Customer
| Assist Customer in setting up initial alerts. Switch alerts: Power loss and Battery voltage for phase 1. |  |  |  |  | Account Manager, Customer
k. Landmarks
| Provide an overview of Landmarks to Customer. |  |  |  |  | Account Manager, Customer
| Provide spreadsheet template to Customer. |  |  |  |  | Account Manager, Customer
| Customer provides spreadsheet with Landmark addresses. |  |  |  |  | Account Manager, Customer
| Add Landmarks via spreadsheet upload, and create landmark groups. |  |  |  |  | Account Manager, Customer
| Review Landmark Mass Update in the portal. |  |  |  |  | Account Manager, Customer
| Add landmark attributes. |  |  |  |  | Account Manager, Customer
Status | 6. Training | Notes | Date Scheduled | Date Completed | Tools | Resources
| The GPS Insight implementation team works with the Customer to define a master software training schedule and identify the training participants who will learn how to use the GPS Insight web portal (admin user). Additional remote (WebEx) training sessions can be scheduled for advanced training and special topics for users. |  |  |  |  | Account Manager
| GPS Insight provides an initial remote (WebEx) product training session(s) for users. Recommend setting up a reoccurring training meeting until all users are trained. |  |  |  |  | Account Manager
| Administrator Training. The initial session typically begins at the administrative level and focuses on establishing a list of users with varying degrees of account/software interface level access. |  |  |  |  | Account Manager
| Non-Administrator Training. Additional training for non-administrative users occurs on dates suggested by the Customer. WebEx meetings can be recorded for playback for any individuals who are unable to attend. |  |  |  |  | Account Manager
| Self-Paced Training. GPS Insight also offers self-paced, online training courses that participants can take on their own time. Using recorded videos and a multiple-choice/interactive quiz, learners can assess how well they meet course objectives. No registration is required. Access the courses from the Help Center. |  |  |  |  | Account Manager
| Quarterly User training and Refresh training sessions. |  |  |  |  | Account Manager
Status | 7. Integration | Notes | Date Scheduled | Date Completed | Tools | Resources
a. Fuel Card Integration
| Provide Customer with Fuel card integration list and data authorization information. |  |  |  |  | Account Manager
| Customer to provide list of vehicles requiring fuel card integration. |  |  |  |  | Customer
| Customer to provide signed approval form for data transmission. |  |  |  |  | Customer
| Account Manager to contact Support for next steps. |  |  |  |  | Account Manager
b. APIs
| Provide an overview of APIs (Application Programming Interface) capabilities to Customer. GPS Insight provides a V2 API for accessing and modifying data directly from your server to ours without the use of our web interfaces. Customers have long been able to use Web APIs to request data from GPS Insight. We provide such Web Services in SOAP and REST formats. We recommend that Customer's developers meet with GPS Insight support prior to utilizing the APIs to discuss specifics. |  |  |  |  | Account Manager
| Access APIs at: http://gpsinsight.com/apidocs |  |  |  |  | Account Manager
b. Webhooks
| Provide an overview of Webhook capabilities to Customer. Webhooks are a simple way to get events in our system (such as a vehicle reporting, or a vehicle entering a landmark, or a driver being assigned) pushed to your system. We push data by making an HTTP POST to a URL that you have configured with us for an event. |  |  |  |  | Account Manager
| Access Webhooks: For details on accessing Webhooks please visit: https://portal.gpsinsight.com/user/webhooks.php. |  |  |  |  | Account Manager
c. GIS Integration
| GPSI Sales Engineer will coordinate GIS Integration with Customer. |  |  |  |  | Account Manager
d. Integration (Other)
| GPS Account Manager to add Integration project here. |  |  |  |  | Account Manager, Sales Engineer
Status | 8. Account Management | Notes | Date Scheduled | Date Completed | Tools | Resources
Overview: We will help with ensuring Customer's achieve maximum ROI with our solution. That includes training, support assistance and account reviews. We understand Customer goals and show them creative ways to use the platform to affect positive change across their organization. We make their goals measurable by turning them into KPIs in account reviews. Below are considerations and best practices:
a. Project Updates
| GPS Insight Account Manager will provide customer with bi-weekly updates during the implementation regarding the implementation progress. This update will include installation, account set up, integration, and training status. |  |  |  |  | Account Manager
a. Customer Meetings
| Provide Customer with an example of a quarterly account review and inquire as to what they would like to see in their account review. |  |  |  |  | Account Manager
| Determine who should attend account reviews with Customer. Recommend all upper management, department heads attend. |  |  |  |  | Account Manager
| Provide an account review at least 2 times a year. |  |  |  |  | Account Manager
| Show New Feature section in Help Center and include in user training meeting. Set a schedule for communicating New Features to Customer. |  |  |  |  | Account Manager
| Determine travel schedule for 2 visits to Customer site per year. |  |  |  |  | Account Manager
c. Device Maintenance
| Once GPS devices are installed there is maintenance that is required on the Customer's part to verify device performance. This includes identifying potential device issues and arranging for service to vehicles for troubleshooting and repair. There are tools available within the GPS Insight Application that customers should use to proactively manage their fleet and devices. We recommend the Customer Fleet Manager, and whomever else is responsible for ensuring the vehicle are running and devices are working correctly, be notified should a vehicle or device need attention. Please see below for the tools we recommend Customers should use and details regarding each. |  |  |  |  | Account Manager, Customer
| Determine communication path for any device issues or system questions/requests. Recommend all device questions are sent to support via email with Account Manager cc'd, and all System related questions are sent/called into Account Manager. Determine if Customer would like to be cc'd on all Support cases. |  |  |  |  | Account Manager
| GPSI to provide Customer with Device Health Analysis at least 2 times a year. |  |  |  |  | Account Manager
| Performance Report scheduled to be delivered weekly to Account Manager and Customer. The Performance report will help Customers quickly identify vehicles that need attention. a. Use this report to see how long vehicles have been stopped and it also shows the last time the device reported. b. “Days Stopped" filter will show vehicles that have been stopped for longer than an acceptable period. c. “Last Reported” filter will show devices that have not reported recently and may be disconnected from power. d. "Battery Voltage" filter will highlight all vehicles that have batteries below a certain threshold to be proactive about potential device issues. |  |  |  |  | Customer
| Battery Voltage Alert set. This will alert when the battery of the vehicle drops below 11.8. Recommend that Customer turns on vehicle or changes battery. |  |  |  |  | Customer
| External Power Lost Alert set. Most GPS devices have short backup batteries and this is a last gasp alert that happens when the device loses external power from vehicle. This alert is great to let Customers know when a battery died or a device has been potentially tampered with or accidentally unplugged. |  |  |  |  | Customer
| Account Manager to send post installation Device Maintenance Program to Customer. Review program and provide recommendations regarding GPSI tools, processes, and invoicing. |  |  |  |  | Account Manager, Customer

## Project Summary Report
GPS Insight Implementation Project Summary Report
|  |  | Customer Name: | 0
[5 empty] | Start Date: | 0
[5 empty] | End Date: | 0
Area | Tasks to Complete | % Complete | Not Started | Complete | In Progress | N/A
1. Contract & Invoicing | 14 | 0% | 14 | 0 | 0 | 0
2. Project Initiation | 12 | 0% | 12 | 0 | 0 | 0
3. Order & Fulfillment | 14 | 0% | 14 | 0 | 0 | 0
4. Installation | 26 | 0% | 26 | 0 | 0 | 0
5. Account Set Up | 77 | 0% | 77 | 0 | 0 | 0
6. Training | 6 | 0% | 6 | 0 | 0 | 0
7. Integration | 10 | 0% | 10 | 0 | 0 | 0
8. Account Management | 13 | 0% | 13 | 0 | 0 | 0
Total: | 172 | 0% | 172 | 0 | 0 | 0